## Sheet1
| Tasks | Additional Considerations
Office Block |  | Done prior to Phase 1.
FALSE | Fill out budget in Invoicing Notes Spreadsheet | Using our downloadable template.
FALSE | Confirm cash is escrowed for upcoming phase. | You'll need to do this for each phase, but we include it here because this is extrememly important before you start the project.
FALSE | Confirm your on-site SOW with contractors for the upcoming phase. | Ask them to send you bids. You'll make any needed adjustments during the pre-phase work for Phase 1.
FALSE | Get keys on-site with lockbox | We recommend making copies of all keys.
FALSE | Pull any necessary permits (building, mechanical, plumbing, electrical) | Typically, the mechanical, plumbing, and electrical permits are pulled by the tradesmen themselves, but you can usually pull your own building permit on a property you own.
FALSE | Turn on utilities. | Be sure to turn off water at the street in case there are any open water lines in the house.
An extra step that costs you nothing is calling 811 to mark all underground utility lines on your property.
FALSE | Begin the pre-phase checklist for Phase 1.
Pre-Phase |  | Tasks repeat at the start of each phase.
FALSE | Have dumpsters delivered. | This is on an as-needed basis.
FALSE | Order materials. | Have them delivered to the job site.
FALSE | Create your Pre-Phase Media Packet. | Take videos and pictures of each job, even if there are overlaps. Add any diagrams needed. You'll be making your Sub Packets out of this information, so include anything needed to educate your subs on the various jobs on the project.
FALSE | Determine your Sub Chunks. | Review the jobs. Which can be "chunked" together?
FALSE | Assign contractors to Sub Chunks. | Which contractors work best for the Sub Chunks you have for the current phase?
FALSE | Prepare Sub Packet(s). | Add all jobs for a particular Sub Chunk into a separate document. This will be the information you give to your contractors when you ask for a bid. Do this for each Sub Chunk within a phase
FALSE | Send Sub Packet(s). | Ask your contractors for bids.
FALSE | Collect all bids from contractors. | Follow up with your contractors to get all bids in hand. Make sure you have written confirmation from your contractors that their bids correspond to your Sub Packet.
FALSE | Adjust your SOW and budget as needed. | Has anything changed now that you have bids in hand?
FALSE | Approve bids. | Make sure and note the bid amounts you're committing to. Get written confirmation from your contractors indicating that the bid has been approved.
FALSE | Schedule contractors. | Get timelines. Note the timlines given to you. You'll need these to hold contractors accountable.
Post-Phase |  | Tasks repeat at the end of each phase.
FALSE | Do a post-phase walkthrough. | Confirm the phase is complete - that the contractor has done his job. You can collect videos and pictures of the completed work for your Post-Phase Media Packet now as well.
FALSE | If contracted work is completed, pay quickly. | Essential for building relationship capital.
FALSE | If contracted work is not completed, put together punchlist. | Deliver ths punchlist to your contractor. This punchlist is an additional level of accountability to your contractor.
FALSE | Create your Post-Phase Media Packet. | Take videos and pictures of the completed work. Note anything that stands out (good or bad). Has the project changed downstream because of the work done? Add these notes to The Ledger.
FALSE | Add any audibles and change orders to the Project SOW. | If needed.
FALSE | Confirm cash is escrowed for upcoming phase. | Things may have changed after any audibles or change orders.
FALSE | Begin the pre-phase checklist for the next phase.
End of Project
FALSE | Run through the 81 Point Checklist. | Do this after Phase 6 as a final check to ensure nothing was missed. If you find something, you may need to call your contractors back.
FALSE | Create your Project Completion Media Packet. | Similar to the Post-Phase Media Packet: take videos and pictures of the final product. Note any pros/cons of the project overall. Would you make any changes to your process on the next project? Add these to The Ledger.